## Template
Sprint Backlog Template
1. User Story one
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | To Do
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Workload Share:
Euan
Heather
Kev
Paddy
Scott

## Backlog
Sprint Backlog
0. Foundation work for preparation of sprint 1
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Set up a spreadsheet | 2 | Heather | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Workload Share:
| Writing up the User stories for My Agility Board | 2 | All | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Euan
| Merging the user stories from everyone | 1 | Scott | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | To Do | Heather
| Wrie up the individual sub tasks for each user story | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | In Progress | Kev
| Write up the accepectance tasks for each user story | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Completed | Paddy
| Organise meeting times and scrum times for Team | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Scott
| Get user stories confirmed with client | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Get tasks and acceptance test confirmed with client | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Get familiar with Git Hub | 10 | All | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Get familiar with Android and JAVA | 15 | All | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Totals |  | 35 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
1. As a developer I require to research available access to the London stock exchange API’s and develop an integration of this for the project to make a central point of access for all other user story requirements
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Research into the available API’s for accessing the London Stock exchange share prices. | 2 |  | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Choose from available options of API’s for Stock Exchange and research integration into android applications. | 3 |  | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research available android API’s for network access to external API’s. | 10 |  | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Design package/classes for use in retrieving the information from API’s. | 12 |  | Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| Research available android API’s for network access to external API’s. | 10 |  | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Implementation of API package/classes | 12 |  | Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| One page document of accessor and mutator methods for created package/classes for reference in building of other classes and packages required for Application. | 1 |  | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 50 |  |  | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
2. As a user I want a notification to alert me when there is a rocket or plummet in my portfolio.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client notification system. | 2 | Scott | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Consider appropriate package placement of the classes required to be built for this functionality. And how they will interlink with other aspects of the sprint stories. | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Research options for UI elements and types of implementation | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Research options for calculation of rockets and plummets | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of the rocket | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Implement code for the backend calculation of the plummet | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 30 |  |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
3.As a user, I want to view my weekly profit or loss in one line so that at a glance I can see how my shares performed this week.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client profit or loss. | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Research options for UI elements and types of implementation | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story | 8 |  | To Do | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research options for calculation of profit or loss | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of profit or loss | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 23 |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
4. As a user, I want to be able to get an update of the value of each set of shares so that I can see how my shares are doing.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Research options for calculation of the share price. | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Design Mockup for the user interface element required to show client breakdown of share set. | 2 |  | To Do
| Implement code for a calculation method for the share price. | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Assess the accessor method to get the data. | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Store the data received in the database to be accessed later. | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Research options for UI elements and types of implementation. | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story. | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 23 |  |  | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
5. As a user, I want a notification of any shares that there is a run for so that I can be up to date.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client notification system. | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Consider appropriate package placement of the classes required to be built for this functionality. And how they will interlink with other aspects of the sprint stories. | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Research options for UI elements and types of implementation | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Research options for calculation of run | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of the run | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 25 |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
6. As a user I want a summary of my best and worst performing shares of the week to keep track of my investments.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client notification system. | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Research options for UI elements and types of implementation | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Research options for calculation method for the worst share price | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Research options for calculation method for the best share price | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of the best share price | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Implement code for the backend calculation of the worst share price | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Assess the accessor method to get the data | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Store the data received in the database to be accessed later | 8 |  | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 |  | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 35 |  |  | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35
7. As a user I want a one line display of the total worth of my portfolio to allow ease of access.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client information. | 2 |  | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Research options for UI elements and types of implementation | 2 |  | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research options for calculation method for the total price | 2 |  | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of the total price | 5 |  | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| One page document of accessor and mutator methods for created package/classes for reference in building of other classes and packages required for Application. | 1 |  | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 12 |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10

## Cycle 1
Sprint Cycle 1
0. Foundation work for preparation of sprint 1
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Set up a spreadsheet | 2 | Heather | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Writing up the User stories for My Agility Board | 2 | All | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Merging the user stories from everyone | 1 | Scott | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Wrie up the individual sub tasks for each user story | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Write up the accepectance tasks for each user story | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Organise meeting times and scrum times for Team | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Get user stories confirmed with client | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Get tasks and acceptance test confirmed with client | 1 | All | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Get familiar with Git Hub | 10 | All | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| Get familiar with Android and JAVA | 15 | All | Completed | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Totals |  | 35 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32
1. As a developer I require to research available access to the London stock exchange API’s and develop an integration of this for the project to make a central point of access for all other user story requirements
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Research into the available API’s for accessing the London Stock exchange share prices. | 2 | Scott | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Choose from available options of API’s for Stock Exchange and research integration into android applications. | 3 | Scott | Completed | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Research available android API’s for network access to external API’s. | 10 | Kev | Completed | 10 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Design package/classes for use in retrieving the information from API’s. | 12 | Kev | Completed | 10 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Research available android API’s for network access to external API’s. | 10 | Scott | Completed | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implementation of API package/classes | 12 | Kev | Completed | 10 | 12 | 7 | 3 | 5 | 0 | 0 | 0 | 0 | 0
| One page document of accessor and mutator methods for created package/classes for reference in building of other classes and packages required for Application. | 1 | Scott | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Totals |  | 50 |  |  | 40 | 36 | 18 | 8 | 7 | 1 | 0 | 0 | 0 | 0
7. As a user I want a one line display of the total worth of my portfolio to allow ease of access.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Design Mockup for the user interface element required to show client information. | 2 | Scott | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research options for UI elements and types of implementation | 2 | Paddy | Completed | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Research options for calculation method for the total price | 2 | Paddy | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Implement code for the backend calculation of the total price | 10 | Heather | Completed | 13 | 10 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0
| One page document of accessor and mutator methods for created package/classes for reference in building of other classes and packages required for Application. | 1 | Euan | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Totals |  | 17 |  |  | 19 | 14 | 9 | 6 | 3 | 1 | 0 | 0 | 0 | 0
Workload Share:
|  | Euan | 30
|  | Heather | 35
|  | Kev | 42
|  | Paddy | 33
|  | Scott | 41

## Cycle 2
3.As a user, I want to view my weekly profit or loss in one line so that at a glance I can see how my shares performed this week.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Update task breakdowns | 1 | Euan | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Research how to implement a burndown chart | 2 | Heather | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Create the Sprint burndown chart | 4 | Heather | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Write up what the team classes as 'done' | 3 | Scott | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Design Mockup for the user interface element required to show client profit or loss. | 2 | Scott | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Confirm the designs with the client | 1 | Kevin | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Research options for UI elements and types of implementation | 2 | Patrick | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story | 8 | Kevin | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Write JUnit Tests | 5 | Euan | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Research options for calculation of profit or loss | 2 | Kevin | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the backend calculation of profit or loss | 8 | Heather | To Do | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Perform black box testing | 5 | Patrick | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Review results of black box testing | 3 | Euan | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Implement any changes from the black box testing | 4 | Scott | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Update the report about testing | 2 | Heather | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Refactor Code | 4 | Kevin | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 | Euan | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 47 |  |  | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47 | 47
4. As a user, I want to be able to get an update of the value of each set of shares so that I can see how my shares are doing.
Priority | Task | Initial Estimation | Who | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| Research options for calculation of the share price. | 2 | Kevin | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Design Mockup for the user interface element required to show client breakdown of share set. | 2 | Euan | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Confirm the designs with the client | 1 | Heather | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Implement code for a calculation method for the share price. | 5 | Scott | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Write Junit Tests | 5 | Patrick | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Assess the accessor method to get the data. | 1 | Patrick | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Store the data received in the database to be accessed later. | 5 | Kevin | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Research options for UI elements and types of implementation. | 2 | Heather | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Implement code for the user interface element of the story. | 5 | Patrick | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Implement black box testing | 5 | Euan | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Review results of black box testing | 3 | Scott | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| Implement any changes from the black box testing | 4 | Kevin | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Update the report about testing | 2 | Heather | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| One page document on any public methods that the classes created may have and also the external classes that it uses | 1 | Euan | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Refactor code | 5 | Kevin | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| Write up final report | 4 | Heather | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Totals |  | 52 |  |  | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52 | 52
Workload Share:
|  |  | Euan | 18
|  |  | Heather | 19
|  |  | Kev | 22
|  |  | Paddy | 18
|  |  | Scott | 22